## Sheet1
 | time axis 2017-06-23 to 2017-08-24
Planning and Preparation
Use Case Scenario | bar: 2017-06-23 to 2017-06-24
Outline of Requirements | bar: 2017-06-23 to 2017-06-24
Use Case Diagram | bar: 2017-06-23 to 2017-06-25
Class Diagrams | bar: 2017-06-23 to 2017-06-26
Risk Analysis | bar: 2017-06-23 to 2017-06-27
Android Class Diagram | bar: 2017-06-24 to 2017-06-27
Market Analysis | bar: 2017-06-24 to 2017-06-28
State Diagrams | bar: 2017-06-25 to 2017-06-26
Technology Analysis | bar: 2017-06-25 to 2017-07-04; 2017-07-20 to 2017-07-27
Technology Research | bar: 2017-06-23 to 2017-06-28; 2017-07-17 to 2017-07-26
Research
Integrate Android Studio with GitHub | bar: 2017-06-23
Setup environment for Android app development | bar: 2017-06-23 to 2017-06-24
Android Research for what's possible | bar: 2017-06-23 to 2017-07-02
Search for exisiting Android templates to use | bar: 2017-06-23 to 2017-07-01
Search for exisiting Android code for modules | bar: 2017-06-28 to 2017-07-15
Application Screen Design
Create Project Screen | bar: 2017-06-24 to 2017-06-25
Project Profile Screen | bar: 2017-06-24 to 2017-06-25
Search Screen | bar: 2017-06-24 to 2017-06-25
Contact/Support Screen | bar: 2017-06-24 to 2017-06-25
User Screen Model | bar: 2017-06-24 to 2017-06-25
Sign Up Screen | bar: 2017-06-25 to 2017-06-26
Splash Screen | bar: 2017-06-25 to 2017-06-26
Profile Screen | bar: 2017-06-25 to 2017-06-26
Home Screen | bar: 2017-06-25 to 2017-06-26
Database
Define primary and seconday keys | bar: 2017-06-29 to 2017-07-01
Outline database structure | bar: 2017-06-29 to 2017-07-04
Set up database hosting | bar: 2017-07-05
Build Database Structure in SQL | bar: 2017-07-05 to 2017-07-11
Connect Database with Application | bar: 2017-07-22 to 2017-07-25
Connet Database with Website | bar: 2017-07-22 to 2017-07-25
Application Screen Implementation
Sign Up Screen | bar: 2017-06-27 to 2017-07-01
Splash Screen | bar: 2017-07-02 to 2017-07-03
Home Screen | bar: 2017-07-04 to 2017-07-06
Create Project Screen | bar: 2017-07-07 to 2017-07-09
Project Profile Screen | bar: 2017-07-10 to 2017-07-12
Search Screen | bar: 2017-07-13 to 2017-07-15
Contact/Support Screen | bar: 2017-07-16 to 2017-07-18
User Profile Screen | bar: 2017-07-19 to 2017-07-21
Website Design & Development
Website Branding and Master Design Template | bar: 2017-06-27 to 2017-07-04
Home Page | bar: 2017-07-05 to 2017-07-08
User Profile Page | bar: 2017-07-09 to 2017-07-11
Project Profile Page | bar: 2017-07-12 to 2017-07-14
Contact / Support Page and search | bar: 2017-07-15 to 2017-07-17
Create Project Page | bar: 2017-07-18 to 2017-07-20
Login / Sign Up Page | bar: 2017-07-21 to 2017-07-23
Design for SEO Page | bar: 2017-08-02 to 2017-08-04
Connections
Sync website with application | bar: 2017-07-27 to 2017-08-05
Testing
Write Sign up screen tests | bar: 2017-06-26
Write Splash screen tests | bar: 2017-07-01
Write Home screen tests | bar: 2017-07-03
Write Create Project Screen tests | bar: 2017-07-06
Write Project Profile Screen tests | bar: 2017-07-09
Write Search function tests | bar: 2017-07-12
Write Contact / Support screen tests | bar: 2017-07-15
Write User profile screen tests | bar: 2017-07-18
Write database to application connection tests | bar: 2017-07-21
Push and pull to database Test | bar: 2017-07-21
Write database to website connection tests | bar: 2017-07-21
Write application to website connection tests | bar: 2017-07-26
Write website to application connection tests | bar: 2017-07-26
Push and pull to database with various types of requests | bar: 2017-07-10 to 2017-07-11; 2017-07-17 to 2017-07-18; 2017-07-24 to 2017-07-25; 2017-07-31 to 2017-08-01; 2017-08-07 to 2017-08-08; 2017-08-14 to 2017-08-15
User testing? TBD